## checkpoint-config
Sl No | Test Case | Status
1 | Open checkpoint-config. The first page offers only Checkpoint or Weigh Bridge. Choose Checkpoint, enter the site network range, and go Next. Software: the saved type is checkpoint and the wizard moves to scan, then devices. Hardware: no coils or readers are driven yet.
2 | Repeat setup as Weigh Bridge, unidirectional. Software: wb_type is unidirectional. Hardware modules later show one front camera plus top, one RFID, and entry/exit lights and booms. Bidirectional cards stay hidden.
3 | Repeat setup as Weigh Bridge, bidirectional. Software: wb_type is bidirectional. Hardware modules show Front-1, Front-2, optional Top, two RFID readers, and four traffic lights. Changing uni to bi clears RFID and traffic-light validation so they must be commissioned again.
4 | On the network scan page, scan the site range. Software: found device IPs can be assigned to RFID, cameras, display, digitizer, and the I/O controller. Go back to the type page and forward again. The chosen type and range are still there.
5 | Checkpoint camera. Software: only the Front camera is required. Check & Save a live RTSP URL. The green tick stays after you leave the page and come back. Finish does not report Camera incomplete. A bad URL does not get a tick.
6 | Unidirectional weighbridge cameras. Software and hardware: cards are Front then Top, both required. Check & Save both live RTSP streams. Both ticks remain. Finish accepts Camera. Top cannot be skipped.
7 | Bidirectional cameras. Software: card order is Front-1, Front-2, then Top. Skip Top. Check & Save Front-1, then Front-2, each with a successful RTSP read. Both front ticks stay, Top stays skipped, and Finish accepts Camera. Typing in Front-2 does not clear Front-1 or the skipped Top.
8 | Unidirectional RFID. Software: one reader. Set IP, API mode, and RFID API port. Check & Save. Hardware: the reader must answer a ping, then a tag presented during the timer is shown. The modal button becomes a tick and Done, not Cancel. The section tick remains after reload.
9 | Bidirectional RFID. Software: Entry A and Entry B have different IPs and different RFID API ports. Check & Save Entry A and read a tag, then Done. Entry A stays validated. Repeat for Entry B. The section tick appears only after both succeed. Saving one side does not clear the other.
10 | RFID negative checks. Software: a reader IP that does not ping is not marked connected, even if some other HTTP port answers. Two bidirectional readers with the same RFID API port are rejected. An empty tag read does not validate the section.
11 | Unidirectional display. Hardware: one display board. Software: Check & Save connects, publishes pcb_id, waits 2 seconds, then publishes data_info/a once. The board shows the test text. data_info/a is not sent twice.
12 | Bidirectional display. Hardware: two boards. Software: first board gets pcb_id a, then 2 seconds later data_info/a once. Second board gets pcb_id b, then 2 seconds later data_info/b once. data_info/a is not published again for the second board.
13 | I/O controller, Ethernet. Hardware: connect the controller and press Connect. Software: after a successful connection, device_ip in the JSON is that controller IP. It is not this computer's LAN address, and it is not written if Connect fails. Finish does not overwrite it.
14 | I/O controller, serial/RTU. Hardware: connect on the commissioned COM port. Software: device_ip in the JSON is that COM port, written only after Connect succeeds.
15 | Traffic lights and boom barriers, Enable off. Hardware: pins do not change and the relay or colour test buttons cannot be clicked. Software: the device is skipped and is not required for Finish.
16 | Traffic lights and boom barriers, Enable on. Hardware: pin fields can be edited and the test buttons drive the real lamp or boom. Software: the device must be tested and saved before the I/O section can validate. Checkpoint requires the entry light. The exit light may be skipped. Weighbridge keeps two boom locations.
17 | Unidirectional I/O layout. Hardware: entry and exit traffic-light cards sit side by side and fill the row. Boom cards sit left to right, not stacked. Sensor test shows entry, weighbridge, and exit inputs changing when each sensor is cut.
18 | Bidirectional I/O layout. Hardware: four traffic lights, Entry A entry, Entry A exit, Entry B entry, and Entry B exit, each with its own Enable. Two booms sit left to right. Direct mode and relay mode each show the matching pin page. The temporary DEBUG PAGE button in I/O help opens that same page for the current direction and output mode.
19 | Duplicate output pins. Software: saving two devices on the same output pin is rejected and names both devices. Hardware: no coil is left half-configured.
20 | Digitizer commissioning. API mode: Check & Save against the digitizer URL and confirm a weight reading. MQTT mode: save broker, weight topic, and request topic. Software: the section validates only after a successful read. Hardware: the live weight matches the scale.
21 | Voice. Software: enable and Check & Save. Hardware: the test clip is heard on the site speaker. If voice is left disabled, Finish still allows it only when the module is not required, and the runtime apps stay silent.
22 | Finish. Software: an incomplete required module is named and Finish does not complete. With every required module validated, Finish saves the JSON. Reload the page: the same ticks are still there. API endpoint editing asks for the admin password. A wrong password does not open it.
23 | Layout. Software: on a wide screen the page uses the full width beside the sidebar. On a phone-width window, cards stack in one column. Light and dark mode keep connected and disconnected badges equally rounded, and camera-modal text stays readable.

## Mines-Checkpoint
Sl No | Test Case | Status
1 | Start Mines-Checkpoint with the commissioned file and demo mode off. Software: the dashboard opens on the application port and shows Scan RFID Card. Hardware: entry light is red and the boom is closed. The display board shows the same idle text.
2 | RFID listen port. Software: the RFID API port from checkpoint-config is open even when it is not the dashboard port. From another PC, POST /rfid_data and GET or POST /rfid_management on that port succeed. If that port is the same as the dashboard port, the app still accepts /rfid_data and does not crash on startup.
3 | Fixed reader, valid tag, gate idle. Hardware: present a site tag on the reader. Software: the tag arrives on the RFID port, cloud validation runs, and the truck number is shown on the dashboard and the display. The reader stops after the tag so it does not keep scanning.
4 | Fixed reader, unknown tag. Hardware: present an unregistered tag. Software: error is shown and announced, the boom stays closed, the light stays red, and the lane returns to Scan RFID Card.
5 | Empty or bad RFID payload. Software: POST /rfid_data with no tag is rejected. The lane does not start and the boom does not move.
6 | Second tag while busy. Hardware: present another tag while the first truck is still being validated. Software: the second tag is ignored and the first trip continues.
7 | Handheld tag. Software: during RFID read, POST /rfid_data_from_mobile_app with a real tag value. A valid tag follows the same cloud check as the fixed reader. A blank value is rejected and the boom stays closed.
8 | ANPR match. Hardware: a truck with a readable plate that matches the tag. Software: the display shows entry granted. Hardware: entry light turns green and the boom opens.
9 | ANPR mismatch. Hardware: plate does not match. Software: the error is shown and announced, and the app waits for office approval. Hardware: boom stays closed until approval. After approval, light goes green and the boom opens. After rejection, the lane returns to idle with the boom closed.
10 | ANPR unreadable. Hardware: plate cannot be read. Software: the unreadable-plate path is announced and the app waits for office approval, same boom rule as a mismatch.
11 | ANPR service down. Software: the dashboard shows a service error, not a raw network dump. Hardware: the boom does not open and the lane returns to idle.
12 | ANPR switched off in configuration. Software: no camera call is made. Office approval is still required before entry. Hardware: the boom opens only after that approval.
13 | Boom permission fails. Software: cloud boom permission returns a failure. Hardware: the boom stays closed and the light stays red.
14 | Crossing sensor. Hardware: with the boom open, cut the sensor and hold it. The boom stays up. Clear the sensor. Software: the trip completes. Hardware: the boom closes after the crossing delay and the light returns to red.
15 | Crossing timeout. Hardware: open the lane, then do not pass a truck. Software: when the wait expires, the lane returns to idle. Hardware: the boom closes without waiting for the crossing delay.
16 | Reset. Software: log in and press Reset during a trip. The reset announcement plays. Hardware: light red, boom closed, display back to Scan RFID Card. Reset and Free Pass stay blocked before login. A wrong password is rejected.
17 | Free pass. Software: after login, start Free Pass. Display shows FREE PASS. Hardware: light green and boom open. After the truck cuts and then clears the sensor, the lane returns to idle with the light red and the boom closed.
18 | Display topic. Hardware: watch the single display. Software: trip text is published only on that display's data_info topic. A pcb_id request from the board still gets the correct letter.
19 | Cloud device address. Software: capture a validate or boom call. device_ip is the I/O controller address saved during commissioning, not this computer's LAN address.
20 | Controller disconnect. Hardware: unplug the I/O controller. Software: the dashboard marks the controller, light, boom, and sensor disconnected. Hardware: the app does not report the lamp or boom as moved while the controller is down. Plug it back in and confirm the next trip drives the lamp and boom again.
21 | Voice. Hardware: confirm the speaker plays the bad-tag clip, the plate-error clip, and the entry announcement. Software: with voice disabled in configuration, the same trips complete with no audio.
22 | Full lane. Hardware and software together: idle, valid tag, cloud accept, plate match, green light, boom up, truck crosses, boom down after the delay, red light, ready for the next truck without restarting the app.

## Mines-WB
Sl No | Test Case | Status
1 | Unidirectional boot, demo mode off. Software: dashboard opens and the display says Enter the Vehicle. RFID is not scanning. Hardware: entry light green, entry boom open, exit light red, exit boom closed. The digitizer live weight is on the dashboard.
2 | Bidirectional boot. Hardware: both booms are open, both entry lights are green, and both exit lights are red. Software: both displays show the idle text. Neither RFID reader is scanning.
3 | Digitizer stream. Hardware: change the scale. Software: every non-zero reading is published on the weight topic, including a repeated value. Put the scale at 0. That 0 is published once, then nothing more is published until the weight changes. Publish any message on the digitizer request topic. The current value is published once on the weight topic, even if it is 0 and was already sent.
4 | Stable weight belongs to Mines-WB. Software: the decoder does not decide stability. The weighbridge accepts a weight only after the configured count of identical readings above 0, default 10. A stream of 0 never becomes the stable weight. A change of value restarts the count.
5 | Idle weight is not 0. Hardware: leave weight on the scale before any truck enters. Software: error_start.wav then Digitizer_error.wav repeats. Cut sensor 1. The trip does not start. On a bidirectional bridge, cut sensor 3 as well. That trip does not start either. Remove the weight so the scale reads 0. The announcement stops, and the next approach-sensor cut starts the trip.
6 | Idle platform fault at 0 kg. Hardware: with the scale at 0, cut the weighbridge sensor and the exit sensor together. Software: the weighbridge fault announcement plays and a new trip does not start. Clear the sensors and the announcement stops.
7 | Unidirectional approach. Hardware: scale at 0, cut only the entry sensor. Software: positioning starts, move-forward is announced, and RFID is still off. Cut only the exit sensor while idle. Software: the lane stays idle.
8 | Bidirectional approach. Hardware: scale at 0. Cut sensor 1. Software: the trip is side A only. Return to idle, then cut sensor 3. Software: the trip is side B only. Cut only the weighbridge sensor while idle. Software: no trip starts.
9 | Weight drops before the truck is alone on the bridge. Hardware: after the approach sensor is cut, roll the truck so the weight rises, then back off so it returns to 0 before only the weighbridge sensor is cut. Software: check-weighbridge is announced and the exit flow starts. A truck that has not yet put any weight on the scale is not sent out just because the reading is still 0.
10 | Position on the bridge. Hardware: while entering, cover the approach sensor and the weighbridge sensor together. Software: weighing does not start yet. Clear the approach sensor so only the weighbridge sensor is cut. Software: weighing starts. If the exit sensor is also cut, the app asks the truck to move back and does not weigh.
11 | Weight capture. Hardware: entry light for the side in use turns red and that boom closes. Software: a stable weight above 5 tonnes goes on to RFID. A stable weight at or below 5 tonnes plays the weight error and returns to idle without starting RFID. If the digitizer does not answer, the digitizer error plays and the lane returns to idle.
12 | RFID after a good weight. Hardware: only the reader on the side the truck entered starts scanning. The other reader stays idle. Software: the first valid tag stops that reader and cloud validation runs. A tag posted on the other reader's port is ignored. No tag before the timeout follows the no-read path. An unknown tag follows the RFID error and then the exit flow.
13 | RFID ports. Software: besides the dashboard port, the unidirectional site has the one configured RFID API port open, and the bidirectional site has both configured RFID API ports open. During RFID read, POST /rfid_data on the port for the side in use is accepted. /rfid_management answers on those ports.
14 | Displays during a trip. Hardware: watch both boards on a bidirectional bridge. Software: trip text is published only to the side the truck entered, data_info/a or data_info/b. The other board keeps the idle text. After the lane returns to idle, both boards show the idle text again. A unidirectional site publishes only its single display topic.
15 | Traffic lights during a trip. Hardware: only the lights on the side in use change. The other side's entry light stays green and its exit light stays red. On exit, the departure side's exit light turns green. When the lane is idle again, both entry lights are green and both exit lights are red.
16 | Booms during a trip. Hardware: the unused side's boom closes when the trip starts so a second truck cannot enter. The side in use closes at weighing and the departure boom is open for exit. After the truck clears the departure sensor, that boom stays up for the crossing delay, then the bidirectional idle state returns with both booms open. A unidirectional exit boom closes after the same delay. If the truck never leaves, the wait expires and the boom closes immediately.
17 | Side B exit sensor. Hardware: a truck that entered from side B must clear the entry sensor to finish, not the exit sensor it entered on. Cutting the entry sensor again before it clears does not finish the trip.
18 | ANPR and weight details. Software: plate match continues to the final weight, posts weight details, and grants exit. Plate mismatch and unreadable plate wait for office handling and play the matching announcement. If the camera service is down, the dashboard shows a service error and the truck is sent to the exit flow without a successful weight posting.
19 | Final weight. Hardware: the truck is still only on the bridge. Software: the final stable weight is announced. A weight outside the allowed band is announced and retried according to the cloud answer. A cloud failure does not show a raw network error on the display.
20 | Free pass. Software: after login, start Free Pass. Hardware: every traffic light is green and every boom is open. After the truck cuts and clears the exit sensor, the lane returns to the correct idle pattern: unidirectional entry open and exit closed, or bidirectional both booms open with entry lights green and exit lights red.
21 | Reset. Software: the Reset button returns the lane to idle and plays the reset announcement. Hardware matches the boot pattern for uni or bi. A cloud reset is sent only when that button is used and the reset flag is enabled. An automatic return to idle does not send it.
22 | Controller and cloud address. Hardware: unplug the I/O controller. Software: lights, booms, and sensors show disconnected. Plug it back in. The next trip drives the correct side. Capture a cloud call: device_ip is the controller address from commissioning, not this computer's LAN address.
23 | Full unidirectional lane. Hardware and software: scale at 0, truck enters, only the weighbridge sensor is cut, stable weight above 5 tonnes, correct RFID, plate accepted, exit light green, truck clears the exit sensor, boom delay, then idle with entry open and exit closed.
24 | Full bidirectional lane, both directions. Run one truck from side A and, after idle, one truck from side B. Each trip uses only that side's reader, that side's display, and that side's traffic lights. The other side is not updated. Both lanes return to both-booms-open idle.